|  | AGENDA ITEM 4 |
| --- | --- |
|  | SSC/04/10 |
| Committee: | Children and Young People Policy and Scrutiny Committee – Safeguarding Sub-Committee |
| Date: | 1 July 2010 |
| In-depth Review of Safeguarding Arrangements – Project Plan |
| Enquiries to: | Graham Redgwell Governance Officer Policy, Community Planning and Regeneration 01245 430360 grahamr@essex.gov.uk |

Project Plan for an In-depth Investigation

| Date | Activity |
| --- | --- |
| 1 July | Group meet to agree pairings and develop their ideas on success indicators - or leave this to the next meeting |
| Late July | Meet with IDeA Social Care Adviser to review their success idicators and discuss potential witnesses |
| August | Graham Redgwell contacts (visits) stakeholder organisations to obtain their co-operation Preparation of bespoke witness guide, based on generic model |
| Sept/October | Terms of Reference agreed by CYP PSC Pairings undertake visits and interview witnesses w/c 20 September Sub-Group Meeting to discuss progress and share process learning 6 October progress report to CYP PSC W/c 18 October Sub-Group meet (with social Care Adviser?) to identify draft findings and recommendations GR and MW to circulate draft findings and recommendations and prepare presentations for workshop |
| November | w/c 8 Nov Stakeholder workshop to test out draft findings and recommendations (Social care Adviser in attendance?) GR and MW draft report |
| December | 1 Dec Sub-Group meet after CYP PSC to consider draft report GR and MW amend report and agree final draft with Sub-Group Chairman |
| January 2011 | Report presented to CYP P&SC |