Report to the Joint Essex Health Overview

and Scrutiny Committee 1st September 2010

3rd August 2010

Author: 		Mandy Ansell – Programme Director

Presented by: 	Barbara Stuttle Deputy Chief Executive and Chief Nurse

- Introduction

NHS South West Essex began its journey to externalising its delivery arm in April 2008 as soon as the policy direction was known.  Initial work focused on delivery arrangements and consultations with stakeholders as to how this would be operationalised.

During the autumn of 2008 joint work was undertaken with NHS SE Essex to look at commissioning capability, service line analysis and reporting and service specifications and care pathways.

In January 2009, following an option appraisals exercise its was agreed that joint work would cease with NHS SE Essex and that a paper would be taken to the PCT Board recommending that a foundation trust would be sought to manage the PCT’s Community Services for a fixed period prior to market testing of all the services.  The partner foundation trust would be identified through a national procurement process; the first of its kind to be undertaken.

The Board formally agreed this option in April 2009.

The tendering process was underpinned by a contestability framework that demonstrated how the PCT would take services to the market and how the transfer to a foundation trust would support this strategy.  Sign off was given by the East of England Strategic Health Authority in July 2009 that the procurement could proceed.

In August 2009 an advert was placed in the Health Service Journal and on Supply2Health requesting expressions of interest from foundation trusts.

The time line for the procurement and integration phases are shown in the attached document:

All the information about the decision making and the process is contained in the attached document:

- Current Status

On the 16th June 2010 the PCT Board agreed to announce North East London Foundation Trust as the preferred bidder.  Work is now underway with the new partner foundation trust (subject to contract) in the following areas:

  - due diligence;

  - organisational transfer and alignment;

  - regulatory requirements through the Competition and Co-operation Panel (CCP) and Monitor;

  - contract agreement and signing.

A joint governance structure has been put in place to deliver the transfer.

- Next Steps

Due to the size of the NELFT submission to Monitor and resultant assessment period a revised timeline has been agreed that will see the final transfer later than 1st November 2010 but well within the government’s timeframe of March 2011.

# Footnotes

please note the handover date of 1st November is being revised due to regulatory requirements.